Technical Assignment for Design

“Reconstruction of Ore Processing Plant, Increasing Capacity to 6 Million Tons of Ore per Year”

| № | List of Main Data and Requirements | Main Data and Requirements |
| --- | --- | --- |
|  | Name and Location of the Facility | Ore Processing Plant, Kazreti settlement, Georgia |
|  | Basis for Design | Decision of the Management Board. |
|  | Type of Construction | Reconstruction |
|  | Design Stages | Basic Technical Solutions (BTS) Project Documentation (PD) Working Documentation (WD) |
|  | Object of Design | Existing Ore Processing Plant |
|  | Level of Responsibility, Complexity of the Facility. | I (high) |
|  | Capacity | Processing plant capacity after reconstruction – 6 million tons of ore per year, consisting of: - Other copper ores – 2.5 million t - Polymetallic ores – 0.5 million t Adopt beneficiation equipment efficiency factor (EEF) 0.9 |
|  | Designed Buildings and Structures, Variant Study at BTS Stage | Buildings and structures at the BTS stage shall be adopted in accordance with Appendix 1 (except for facilities for polymetallic ore processing). Economic calculations and selection of options are carried out by the Client. Based on BTS results and selected options refine the list of buildings and structures for further design. |
|  | Processing Technology | Gravity-flotation beneficiation Appendix 2 provides a preliminary technological scheme for processing copper ores of the Dambludi deposit. Subject to adjustment based on BTS results. |
|  | Requirements for Developing BTS | Develop preliminary solutions: - Water-slurry and P&ID schemes - Selection of technological equipment, specification - Layout solutions (main plans, sections) - Staffing schedule - Power consumption calculation - Situational plan |
|  | Requirements for Developing Project Documentation (PD) | Project documentation must comply with European standards |
|  | Requirements for Developing Work Documentation (WD) | Develop the following WD sections: TX (Technological Section), AR (Architectural Section), KM (Metal Structures), RC (Reinforced Concrete Structures), PS (Power Supply), EE (Electrical Equipment), ATX (Automation & Control) |
|  | Initial Data from the Client | - 1. Existing technological, water-slurry schemes, and apparatus chain diagram; - Preliminary technological regulations (Dambludi deposit); - Water chemical analysis for fluidization process; - Technical data on existing engineering systems (water, air, reagents); - Soil engineering-geological survey for reconstruction; - Plans and sections of existing sites within reconstruction boundaries; - BTS on gravity processing for other copper ores. |
|  | Deadlines | BTS – no more than 3 months PD – no more than 5 months after BTS WD – no more than 5 months after PD, with phased submission |
|  | Project Approvals and Expertise | - Documentation to be agreed with the Client. - Expertise and approval by state authorities are carried out by the Client. - Author’s supervision is not required. |
|  | Requirements for Submitting the Technical and Commercial Proposal (TCP) | - Indicate the cost of design works by type of work and by design object (buildings and structures); working documentation – including by sections; The cost of PD and WD will be adjusted based on BTS results due to refinement of the list of designed buildings and structures. - Reference list in the mining sector, including client feedback on completed projects; - CVs of involved specialists; |

Prepared by:

Deputy Managing Director for Production Projects

______________ Alexander Patrakeev
“______” _______________ 2025