TERMS OF REFERENCE (TOR): DETAILED ENGINEERING DESIGN FOR THE NEW MTKVARI RIVER PIPELINE BRIDGE

1. OBJECTIVE OF THE ASSIGNMENT

To contract expert engineering services for the preparation of a Detailed Construction Design for a new pipeline bridge over the Mtkvari River (approx. 531.73 m). The project aims to deliver an optimized, constructible, and durable structural solution to support two DN 800 mm pipelines and a technical walkway.

The design shall ensure a minimum service life of 50 years, extendable through a defined maintenance strategy.

2. DESIGN STAGES AND QUALITY ASSURANCE

Design Stages:

- 30% Concept Design

- 60% Detailed Design

- 100% Final Design (For Construction)

Design Review & QA:
The Consultant shall implement a formal internal Quality Assurance system, including:

- Independent design verification (Four-Eyes Principle)

- Documented checking procedures for all calculations and drawings

Design Optimization Requirement:
The Consultant shall optimize the structural solution to minimize CAPEX and OPEX while ensuring safety, durability, and constructability.

Alternative Analysis (Mandatory):
At the 30% stage, the Consultant shall develop and assess at least two alternative structural typologies, including a comparative evaluation based on:

- Structural efficiency

- Cost

- Constructability

- Maintenance requirements

A recommended solution shall be justified and submitted for approval.

Value Engineering:
The Consultant shall identify and quantify at least three value engineering proposals during the design process.

3. SCOPE OF ENGINEERING SERVICES

A. Site Investigations & Ground Testing

- Geotechnical & Geophysical Study: Boreholes, SPT, and laboratory testing to define foundation parameters and seismic soil classification.

- Hydrological Study: Flood discharge analysis (Q100/Q500), including:

  - Minimum required freeboard

  - Hydraulic forces on structural elements

  - Scour depth and protection measures

  - Assessment of floating debris impact

B. Structural Modeling & Design (FEM)

- 3D FEM Analysis: Development of a full 3D structural model including interaction between pipelines, structural elements, and bearings.

- Staged Construction Analysis: Verification of stresses and stability during all erection phases.

Design Loads Definition (Eurocode-based):

- Self-weight (including coatings)

- Internal water load and operating pressure

- Loads from fittings and ancillaries

- Seismic actions (Eurocode 8 and Georgian Standards)

- Wind loads

- Thermal expansion and gradients

Design Standards:
Design shall be based on relevant Eurocodes, including:

- EN 1990 (Basis of Design)

- EN 1991 (Actions on Structures)

- EN 1992/1993 (depending on material)

- EN 1998 (Seismic Design)

Fatigue Analysis (Mandatory):
Fatigue verification shall be performed considering cyclic loading due to operational and environmental conditions.

Pipeline–Structure Interaction:
The design shall clearly define:

- Anchor points and restraint systems

- Expansion philosophy

- Pipe support configuration (fixed, guided, sliding)

- Thermal movement accommodation

Bearings Design:
Specification of bearing systems considering:

- Thermal movements

- Seismic displacements

- Long-term maintenance and replacement strategy

C. Pipeline & Walkway Engineering

- Hydraulic Design: Steady-state and transient (water hammer) analysis

- Ancillary Systems: Air valves, drainage points, anchorage forces

- Inspection Walkway:

  - Lightweight galvanized steel structure

  - Structurally independent from pipelines

  - Sliding connections to accommodate thermal expansion

- Durability Design:

  - Corrosion allowance definition

  - Coating system (minimum C5-M environment)

  - Defined inspection and maintenance intervals

D. Construction Methodology (Mandatory)

The Consultant shall provide a fully detailed construction methodology, including:

- Erection sequence (step-by-step)

- Pipeline installation procedure

- Temporary works and support structures

- Access platforms and construction logistics

Constructability Constraints:
The design shall consider:

- Access limitations from riverbanks

- Restrictions on in-river works (if applicable)

- Feasibility of crane operations and lifting strategies

- Environmental protection requirements during construction

4. OPERATIONAL AND ENVIRONMENTAL CONSTRAINTS

Environmental Protection:
The design shall include specific measures for:

- Debris containment systems

- Pollution prevention procedures

- Safe working platforms over the river

Service Continuity:
The existing water supply shall remain uninterrupted until final tie-in.

5. FINAL DELIVERABLES (CONSTRUCTION TENDER PACKAGE)

The Consultant shall deliver a complete “For Construction” level design, including:

- Design Basis Report (DBR)

- Detailed Calculation Report (including editable FEM model files)

- Construction Drawings (For Construction level) with full execution detail

- Method Statement (construction and installation procedures)

- Bill of Quantities (BOQ):

  - Editable format

  - Structured by work chapters

  - Based on SIP pricing methodology

  - Including clear measurement rules

- Project Risk Register

- Post-Construction Preventive Maintenance Plan

6. CONSULTANT EXPERIENCE

The Consultant shall demonstrate proven experience in:

- Design of bridges or pipe bridges with spans or total lengths >100 m

- Seismic design in high-risk zones

- Delivery of international infrastructure projects of similar complexity

7. DESIGN LIFE AND MAINTENANCE STRATEGY

The structure shall be designed for a minimum service life of 50 years, supported by:

- Defined inspection intervals

- Maintenance procedures

- Accessibility to critical components (bearings, supports, anchors, valves)

The design shall ensure that key elements can be inspected, maintained, and replaced without major service disruption.

END OF TERMS OF REFERENCE