## VOLUMES
Road Volumes |  |  |  |  | Platform Volumes |  |  |  | Foundation Volumes (Estimated) |  |  |  | Reloading Platform Volume
Road | Cut(m3) | Fill (m3) | Length(m) | Max-Slope | Platform | Cut (m3) | Fill (m3) | Elevation (m) | Turbine No | Foundation Concrete | Cut M3 | Back Fill M3 | Platform | Cut (m3) | Fill (m3) | Elevation (m)
RS01 | 2359 | 7982 | 475 | 12.17 | T01 | 50651 | 38630 | 572 | T01 | 600 | 2130 | 1530 | Reloading Platform | 14000 | 11500 | 215
RS02 | 7647 | 11665 | 675 | 11.04 | T02 | 16351 | 50530 | 630 | T02 | 600 | 2130 | 1530
RS03 | 1650 | 6739 | 175 | 7.7 | T03 | 49522 | 30720 | 714 | T03 | 600 | 2130 | 1530
RS04 | 4171 | 12804 | 650 | 12.56 | T04 | 12601 | 27162 | 756 | T04 | 600 | 2130 | 1530
RS05 | 3735 | 1561 | 575 | 11.57 | T05 | 27881 | 29264 | 805 | T05 | 600 | 2130 | 1530
RS06 | 425 | 6676 | 550 | 10.68 | T06 | 18660 | 10468 | 864 | T06 | 600 | 2130 | 1530
RS07 | 56 | 20513 | 750 | 10.79 | T07 | 43186 | 27877 | 969 | T07 | 600 | 2130 | 1530
RS08 | 2370 | 21890 | 990 | 12.04 | T08 | 38515 | 37310 | 975 | T08 | 600 | 2130 | 1530
RS09 | 4344 | 21687 | 740 | 10.8 | T09 | 24353 | 41322 | 864 | T09 | 600 | 2130 | 1530
RS10 | 6005 | 6665 | 825 | 8.5 | T10 | 45209 | 3705 | 869 | T10 | 600 | 2130 | 1530
RS11 | 10006 | 7295 | 1500 | 11.6 | T11 | 28995 | 35023 | 845 | T11 | 600 | 2130 | 1530
RS12-1-2 | 5156 | 531 | 125 | 7.6 | T12 | 31715 | 23305 | 841 | T12 | 600 | 2130 | 1530
RS12-3 | 1250 | 552 | 60 | 7.1 | T13 | 56021 | 42595 | 775 | T13 | 600 | 2130 | 1530
RS13 | 72 | 18643 | 250 | 6.18 | T14 | 19847 | 24642 | 920 | T14 | 600 | 2130 | 1530
RS14 | 1243 | 9283 | 650 | 10.95 | T15 | 29808 | 18622 | 938 | T15 | 600 | 2130 | 1530
RS15 | 799 | 15820 | 175 | 7.94 | T16 | 14523 | 11714 | 994 | T16 | 600 | 2130 | 1530
RS16 | 20217 | 16879 | 525 | 12.2 | T17 | 21318 | 61502 | 1073 | T17 | 600 | 2130 | 1530
RS17 | 3158 | 3057 | 400 | 11.51 | T18 | 56512 | 46862 | 1072 | T18 | 600 | 2130 | 1530
RS18 | 991 | 19214 | 400 | 9.64 | T19 | 17639 | 22627 | 1155 | T19 | 600 | 2130 | 1530
RS19 | 10597 | 11755 | 1000 | 8.38 | T20 | 32219 | 29707 | 1155 | T20 | 600 | 2130 | 1530
RS20 | 6455 | 10221 | 700 | 11.52 | T21 | 21041 | 9513 | 1201 | T21 | 600 | 2130 | 1530
RS21 | 25119 | 23018 | 1490 | 10.68 | T22 | 17461 | 9376 | 1251 | T22 | 600 | 2130 | 1530
RS22 | 23924 | 60161 | 1260 | 12.02 | T23 | 10494 | 8454 | 1227.5 | T23 | 600 | 2130 | 1530
RS23 | 5795 | 46455 | 500 | 11.06 | T24 | 9761 | 8564 | 1215 | T24 | 600 | 2130 | 1530
RS24 | 65949 | 29044 | 3030 | 11.86 | T25 | 61719 | 39181 | 1075 | T25 | 600 | 2130 | 1530
RS25 | 9963 | 27447 | 950 | 11.47 | Switchyard | 65057 | 10746 | 900 | Total | 15000 | 53250 | 38250
RS26 | 30818 | 12342 | 1525 | 11.83 | Service Area | 917 | 1878 | 891
RS27 | 4448 | 17476 | 550 | 11.87 | Total | 821976 | 701299
RS28 | 2677 | 10518 | 650 | 6.98
RS29 | 3450 | 5435 | 520 | 11.55
RS30 | 1161 | 6684 | 315 | 11.79
ARS-01-1 | 37789 | 12071 | 1350 | 12.51
ARS-01-2 | 981 | 4929 | 825 | 12.49 |  |  | TOTAL VOLUME (ROAD+PLATFORM+FOUNDATION)
Intersection-1 | 56 | 76 | 40 | 16.37 |  |  | CUT M3 | 1182261
Intersection-2 | 72 | 106 | 60 | 14.02 |  |  | FILL M3 | 1182261
Intersection-3 | 36 | 539 | 60 | 8.49
Intersection-4 | 4 | 1363 | 50 | 17.76
Intersection-5 | 37 | 1062 | 140 | 11.75
Intersection-6 | 2050 | 1888 | 400 | 15.45
Total | 307035 | 492046

## ROAD VOL
Gogni WPP Road Works – Summary Table | [7 empty] | Road Width (m) | Subbase Thickness (m) | Base Thickness (m)
No. | Route | Road Length (m) | Excavation (m³) | Fill (m³) | Topsoil Clearing (m²) | Subbase Layer – 30 cm | Base Layer – 20 cm | 8 | 0.3 | 0.2
1 | RS01 | 475 | 2359 | 7982 |  | 1140 | 760
2 | RS02 | 675 | 7647 | 11665 |  | 1620 | 1080
3 | RS03 | 175 | 1650 | 6739 |  | 420 | 280
4 | RS04 | 650 | 4171 | 12804 |  | 1560 | 1040
5 | RS05 | 575 | 3735 | 1561 |  | 1380 | 920
6 | RS06 | 550 | 425 | 6676 |  | 1320 | 880
7 | RS07 | 750 | 56 | 20513 |  | 1800 | 1200
8 | RS08 | 990 | 2370 | 21890 |  | 2376 | 1584
9 | RS09 | 740 | 4344 | 21687 |  | 1776 | 1184
10 | RS10 | 825 | 6005 | 6665 |  | 1980 | 1320
11 | RS11 | 1500 | 10006 | 7295 |  | 3600 | 2400
12 | RS12-1-2 | 125 | 5156 | 531 |  | 300 | 200
13 | RS12-3 | 60 | 1250 | 552 |  | 144 | 96
14 | RS13 | 250 | 72 | 18643 |  | 600 | 400
15 | RS14 | 650 | 1243 | 9283 |  | 1560 | 1040
16 | RS15 | 175 | 799 | 15820 |  | 420 | 280
17 | RS16 | 525 | 20217 | 16879 |  | 1260 | 840
18 | RS17 | 400 | 3158 | 3057 |  | 960 | 640
19 | RS18 | 400 | 991 | 19214 |  | 960 | 640
20 | RS19 | 1000 | 10597 | 11755 |  | 2400 | 1600
21 | RS20 | 700 | 6455 | 10221 |  | 1680 | 1120
| RS21 | 1490 | 25119 | 23018 |  | 3576 | 2384
| RS22 | 1260 | 23924 | 60161 |  | 3024 | 2016
| RS23 | 500 | 5795 | 46455 |  | 1200 | 800
| RS24 | 3030 | 65949 | 29044 |  | 7272 | 4848
| RS25 | 950 | 9963 | 27447 |  | 2280 | 1520
| RS26 | 1525 | 30818 | 12342 |  | 3660 | 2440
| RS27 | 550 | 4448 | 17476 |  | 1320 | 880
| RS28 | 650 | 2677 | 10518 |  | 1560 | 1040
| RS29 | 520 | 3450 | 5435 |  | 1248 | 832
| RS30 | 315 | 1161 | 6684 |  | 756 | 504
| ARS-01-1 | 1350 | 37789 | 12071 |  | 3240 | 2160
| ARS-01-2 | 825 | 981 | 4929 |  | 1980 | 1320
| Intersection-1 | 40 | 56 | 76 |  | 96 | 64
| Intersection-2 | 60 | 72 | 106 |  | 144 | 96
22 | Intersection-3 | 60 | 36 | 539 |  | 144 | 96
23 | Intersection-4 | 50 | 4 | 1363 |  | 120 | 80
24 | Intersection-5 | 140 | 37 | 1062 |  | 336 | 224
25 | Intersection-6 | 400 | 2050 | 1888 |  | 960 | 640
TOPLAM |  | 25905 | 307035 | 492046 | 0 | 62172 | 41448

## SUMMARY
Summary Table of BOQ for Gogni WPP Construction Works
No. | Description of Work | Quantity | Unit | Unit Price |  | Total Amount (USD) | Cumulative Percentage %
1 | ROADS | 25905 | meter | 0 | USD/m | 0 | #DIV/0!
2 | HARDSTANDS | 25 | pcs | 0 | USD/pcs | 0 | #DIV/0!
3 | TURBINE FOUNDATION | 25 | pcs | 0 | USD/pcs | 0 | #DIV/0!
4 | TRAFFIC SIGNS AND TURBINE FENCE WORKS | 1 | lot | 0 | USD | 0 | #DIV/0!
5 | RELOADING AREA | 1 | lot | 0 | USD | 0 | #DIV/0!
6 | SWITCHYARD AND STORAGE AREA | 1 | lot | 0 | USD | 0 | #DIV/0!
7 | OPTIONAL | 1 | lot | 0 | USD | 0 | #DIV/0!
GRAND TOTAL (USD) | [5 empty] | 0

## 1-ROADS
Gogni WPP - Access and Service Roads - BoQ
Total Road Length:25230m
Item No | Type of Work | Unit | Quantity | Unit Price (USD) | Total Amount (USD)
R-01 | Cleaning and dismantling with machinery in excavation and backfill areas | m² | 437360 |  | 0
R-02 | Machine excavation of all types of ground | m³ | 307035 |  | 0
R-03 | Machine filling of all types of ground | m³ | 492046 |  | 0
R-04 | Sub-base coating (using suitable material from excavation or externally supplied) | m³ | 62172 |  | 0
R-05 | Base layer (coating) construction (including transport, material, spreading, watering, compaction, Granular Base Layer PMT) | m³ | 41448 |  | 0
GRAND TOTAL (USD) |  |  |  |  | 0
Road Cost per Meter (USD) |  |  |  |  | 0

## 2-HARDSTANDS
Gogni WPP - Hardstands - BoQ | [5 empty] | Subbase Thickness (m) | Base Thickness (m)
Item No | Type of Work | Unit | Quantity | Unit Price (USD) | Total Amount (USD) | 0.3 | 0.2
HS-01 | Cleaning and dismantling with machinery in excavation and backfill areas | m² | 0 |  | 0
HS-02 | Machine excavation of all types of ground | m³ | 821976 |  | 0
HS-03 | Machine filling of all types of ground (with proper compacting) | m³ | 400000 |  | 0
HS-04 | Machine filling of all types of ground (for stock) | m³ | 312930 |  | 0
HS-05 | Sub-base coating (using suitable material from excavation or externally supplied) | m³ | 99691.2 |  | 0
HS-06 | Base layer (coating) construction (including transport, material, spreading, watering, compaction, Granular Base Layer PMT) | m³ | 66460.8 |  | 0
|  | Total Platform Cost (USD) |  |  | 0

## 3-FOUNDATIONS
Gogni WPP - Turbine Foundation Construction Works – BOQ
Foundation Works BOQ (per 1 Foundation)
Item No | Type of Work | Unit | Quantity | Unit Price (USD) | Total Amount (USD)
F-01 | Machine excavation of all types of ground | m³ | 2130 |  | 0
F-02 | C16/20 Concrete (including materials, transportation, pumping, labor, etc.) | m³ | 45 |  | 0
F-03 | C40/50 Ready-Mix Concrete (including materials, transportation, pumping, labor, etc.) | m³ | 943.59 |  | 0
F-04 | Backfilling (min. Compaction 18 kN/m³) | m³ | 1530 |  | 0
F-05 | Reinforced Concrete Formwork (including materials, transportation, labor, etc.) | lot | 1 |  | 0
F-06 | Ø14–Ø40 mm S420a Reinforcement Steel (including materials, transportation, labor, etc.) | ton | 108 |  | 0
F-07 | Ø55 mm HDPE PN6 Dranaige Pipe Installation | m | 15 |  | 0
F-08 | Foundation total surface insulation with bitumen-based liquid insulation material. | lot | 1 |  | 0
F-09 | Insulation of Foundation's Pedestal area using BASF-Masterseal 550 (seal) isolation + UV protected membrane or with similar approved material and technology | lot | 1
F-10 | Anchor Cage Installation | lot | 1 |  | 0
F-11 | Foundation Base Perimeter Drainage and Associated Works (including excavation for pipe outlet and pipe) (Ø160 Perforated Pipe, Geotextile, Gravel) | m | 76.0265 |  | 0
F-12 | Grouting at Foundation–Steel Tower Interface, Grout C90/105 (using BASF MasterFlow 9200 or equivalent and BASF MasterSeal 550; including material supply, installation labor, and all horizontal/vertical transportation) | m³ | 1 |  | 0
F-13 | Pad-mounted transformer foundation (including materials, transportation, labor, etc.) according to Gogni WPP Project | lot | 1 |  | 0
F-14 | Foundation Earthing Works according to Gogni WPP Earthing Project | set | 1 |  | 0
Total Cost per 1 Foundation (USD) |  |  |  |  | 0
Note: Quantity calculations have been carried out based on the GWH-182 sample foundation design as a reference.
BASF-Masterseal 550 (seal) İzolasyon + UV dayanimli membran

## 4-TRAFIC SIGNS & TRB FENCE
Gogni WPP - Traffic Signs and Turbine Fence Works – BOQ
Item No | Type of Work | Unit | Quantity | Unit Price (USD) | Total Amount (USD)
TR-01 | Identification and Design of Vertical Traffic Markings on Project Roads According to the Standards Supply of Traffic Signs in Compliance with Highway Technical Specifications, Installation, Maintenance During Construction, and Handover to the Employer upon Completion. | pcs | 1 |  | 0
TR-02 | Supply and Installation of Fiberglass Reinforced Polyester (FRP) Roadside Posts along Main and Turbine Access Roads, in accordance with the project and the relevant provisions of the Highway Technical Specifications. | pcs | 1 |  | 0
TR-03 | Supply and Installation of Snow Poles along Main and Turbine Access Roads, in compliance with the Highway Technical Specifications (2" diameter steel pipe posts, painted at the base with 100 cm white and alternating 50 cm black–orange–black stripes, with reflective material every 50 cm along the post). | pcs | 1 |  | 0
TR-04 | Supply and Installation of Turbine Warning and Information Signs with Posts for Each Turbine. Additionally, turbine numbering on circular transparent stickers (60 cm diameter, Arial font, blue text) applied on the turbine. | pcs | 1 |  | 0
TR-05 | Installation of galvanized panel fencing (including fences. foundation. galvanized door. razor vire) | lot | 1 |  | 0
Total (USD) |  |  |  |  | 0

## 5- RELOADING AREA
Gogni WPP - Blade Reloading Area - BoQ | [5 empty] | Subbase Thickness (m) | Base Thickness (m)
Item No | Type of Work | Unit | Quantity | Unit Price (USD) | Total Amount (USD) | 0.3 | 0.2
RA-01 | Cleaning and dismantling with machinery in excavation and backfill areas | m² | 14000 |  | 0
RA-02 | Machine excavation of all types of ground | m³ | 14000 |  | 0
RA-03 | Machine filling of all types of ground (with proper compacting) | m³ | 11500 |  | 0
RA-04 | Sub-base coating (using suitable material from excavation or externally supplied) | m³ | 4200 |  | 0
RA-05 | Base layer (coating) construction (including transport, material, spreading, watering, compaction, Granular Base Layer PMT) | m³ | 2800 |  | 0
|  | Total Platform Cost (USD) |  |  | 0

## 6- Switchyard and storage area
Gogni WPP - Switchyard and Storage Area - BoQ | [5 empty] | Subbase Thickness (m) | Base Thickness (m)
Item No | Type of Work | Unit | Quantity | Unit Price (USD) | Total Amount (USD) | 0.3 | 0.2
RA-01 | Cleaning and dismantling with machinery in excavation and backfill areas | m² | 17000 |  | 0
RA-02 | Machine excavation of all types of ground | m³ | 65974 |  | 0
RA-03 | Machine filling of all types of ground (with proper compacting) | m³ | 12624 |  | 0
RA-04 | Sub-base coating (using suitable material from excavation or externally supplied) | m³ | 5100 |  | 0
RA-05 | Base layer (coating) construction (including transport, material, spreading, watering, compaction, Granular Base Layer PMT) | m³ | 13194.8 |  | 0
|  | Total Platform Cost (USD) |  |  | 0

## OPTIONAL
Gogni WPP - Optional Civil Structures - BoQ
Item No | Type of Work | Unit | Quantity | Unit Price (USD) | Total Amount (USD)
OPT-1 | Installation of Ø400 mm nominal diameter corrugated pipe, made of High-Density Polyethylene (HDPE) and Polypropylene (PP) (SN 8), including materials, transportation, excavation, backfill, and labor. | m | 1 |  | 0
OPT-2 | Installation of Ø600 mm nominal diameter corrugated pipe, made of High-Density Polyethylene (HDPE) and Polypropylene (PP) (SN 8), including materials, transportation, excavation, backfill, and labor. | m | 1 |  | 0
OPT-3 | Installation of Ø800 mm nominal diameter corrugated pipe, made of High-Density Polyethylene (HDPE) and Polypropylene (PP) (SN 8), including materials, transportation, excavation, backfill, and labor. | m | 1 |  | 0
OPT-4 | Installation of Ø10000 mm nominal diameter corrugated pipe, made of High-Density Polyethylene (HDPE) and Polypropylene (PP) (SN 8), including materials, transportation, excavation, backfill, and labor. | m | 1 |  | 0
OPT-5 | Supply and installation of Ø1000 mm steel pipe for drainage purposes, including excavation, bedding, installation, welding/jointing, backfilling, and all associated works. | m | 1 |  | 0
OPT-6 | Construction of reinforced concrete retaining wall with variable thickness (20–50 cm), including excavation, formwork, reinforcement, concrete works, backfilling, drainage provisions, and all associated works. | m³ | 1 |  | 0
OPT-7 | Construction of gabion retaining wall, including supply and installation of gabion baskets, filling with approved stone material, foundation preparation, geotextile (if required), and all associated works. | m³ | 1 |  | 0
OPT-8 | Construction of modular concrete block (lego-type) retaining wall, including supply, placement, leveling, and all necessary stabilization works. | m³ | 1 |  | 0
OPT-9 | Construction of reinforced concrete road pavement, including subgrade preparation, formwork, reinforcement, concrete casting, curing, joints, and finishing works. | m³ | 1 |  | 0
OPT-10 | Cutting, filling, grading, and compaction of storage or working areas in accordance with approved design, including disposal of excess material and import of suitable fill where required. (For Site Compound Area) | m³ | 1 |  | 0
OPT-11 | Construction of site compound area including installation of containers (office, storage, sanitary), internal roads, parking areas, fencing, lighting, and provision of utilities (water supply, wastewater system, electricity), all in accordance with approved design. | Unit | 1 |  | 0
OPT-12 | Excavation of 5-6th category soil according to SNiP (СНиП) norms | m³ | 1 |  | 0
OPT-13 | Excavation of 7th and higher category soil according to SNiP (СНиП) norms | m³ | 1 |  | 0
OPT-14 | Implentation of geotextile to separate different soil layers and maintain water filltration (passage) 500gr/sq.m | m2 | 1
OPT-15 | Implentation of triaxial geogrid to separate different soil layers and maintain water filltration (passage) with minimumtensile strength 40 KN/m | m2 | 1 |  | 0
OPT-16 | Implementing Geogrid for slope stabilization 200 gr/sq.m | m2 | 1 |  | 0
Total (USD)