## 路基工程最终拟定劳务工作量价格清单
附件-三工区土石方专业分包工作量价格清单 Attachment – Schedule of Prices for Earthwork & Rockwork Professional Subcontracting – Work Zone 3 | [9 empty] | 拉里人民币汇率 | 2.6135
清单细目编号 Item No. | 清单细目名称 Description of Item | 单位 Unit | 工程量Quantity | 最终合同价 （不含税） Final Contract Rate (excl. VAT) |  | 主要工作内容 Scope of Work | 费用组成 Cost Composition | 计量规则 Measurement Rules | 备注Remarks
|  |  |  | 单价 Unit Rate (GEL) | 小计 Total （GEL）
1 | 土方开挖 | BCM | 320000 |  | 0 | 普通土的开挖、装车、运输至投标人自选的合法弃渣场、场内推平压实、全流程环保管理。包含施工期间的临时边坡修整、临时排水沟开挖及维护、开挖面及运输道路的临时防排水措施。 Excavation of ordinary soil, loading, and transport to the legal spoil disposal site selected by the Subcontractor, including spreading and compaction within the disposal site, and full-process environmental management. Also includes temporary slope trimming, excavation and maintenance of temporary drainage ditches, and temporary surface and haul road drainage measures during construction. | 综合单价为全费用全运距单价。数量为暂估，按实结算。 The unit rate is an all-inclusive rate covering all costs and all haul distances. The quantity is provisional and subject to adjustment based on actual measured work. | 按设计断面面积， 以天然方体积计算 Measured in natural cubic metres (BCM) based on the designed cross-sectional area. | 40% |  |  | 10+500-12+300:82 12+300-12+440:1.5 1+260-1+380：0.2 T2+T3出口：1 | 84.7
2 | 软石开挖 | BCM | 320000 |  | 0 | 软石/次坚石的开挖（含机械破碎）、装车、运输至投标人自选的合法弃渣场、场内推平压实、全流程环保管理。包含施工期间的临时边坡修整、临时排水沟开挖及维护、开挖面及运输道路的临时防排水措施。 Excavation of soft rock / hard soil (including mechanical breaking), loading, and transport to the legal spoil disposal site selected by the Subcontractor, including spreading and compaction within the disposal site, and full-process environmental management. Also includes temporary slope trimming, excavation and maintenance of temporary drainage ditches, and temporary surface and haul road drainage measures during construction. | 综合单价为全费用全运距单价。数量为暂估，按实结算。 The unit rate is an all-inclusive rate covering all costs and all haul distances. The quantity is provisional and subject to adjustment based on actual measured work. | 按设计断面面积， 以天然方体积计算 Measured in natural cubic metres (BCM) based on the designed cross-sectional area. | 40% |  |  | B4渣土转运约3.2万
3 | 坚石爆破开挖 | BCM | 160000 |  | 0 | 需爆破的坚硬岩石（含钻孔、爆破手续、炸药、安全防护）、开挖、装车、运输至投标人自选的合法弃渣场、场内推平压实、全流程环保管理。包含施工期间的临时边坡修整、临时排水沟开挖及维护、开挖面及运输道路的临时防排水措施。 Excavation of hard rock by blasting (including drilling, all licences/permit applications, explosives supply, and safety protection), loading, and transport to the legal spoil disposal site selected by the Subcontractor, including spreading and compaction within the disposal site, and full-process environmental management. Also includes temporary slope trimming, excavation and maintenance of temporary drainage ditches, and temporary surface and haul road drainage measures during construction. | 综合单价为全费用全运距单价。数量为暂估，按实结算。 The unit rate is an all-inclusive rate covering all costs and all haul distances. The quantity is provisional and subject to adjustment based on actual measured work. | 按设计断面面积， 以天然方体积计算 Measured in natural cubic metres (BCM) based on the designed cross-sectional area. | 20%
合计（不含税） Subtotal (excl. VAT) |  | GEL |  |  | 0
增值税 VAT |  | GEL |  |  | /
税价合计 Total incl. VAT |  | GEL |  |  | 0

## 路基工程最终拟定劳务工作量清单 (hidden)
附件BC01-路基工程一阶段及T2隧道明挖拟定劳务工作量清单 | [9 empty] | 拉里人民币汇率 | 2.6135
清单细目编号 | 清单细目名称 | 单位 | 主合同 约定数量 | 1号补充协议 变更量 | 变更后 工程量 | 主要工作内容 | 费用组成 | 计量规则 | 备注
1 | 路基清表 | m2 | 153601.6 |  | 153601.6 | 20cm厚表土清除（含杂物植被）,1km内运输堆放以备再利用,填方区域清表后的平整,碾压。 | 机械清除表土20cm厚，挖、装、运、卸至甲方指定地点的等一切工作内容（只限于填方段） | 路基边坡红线界间面积计算
2 | 土方开挖 | m3 | 251210.94 | 630464.87 | 881675.81 | 清理现场、挖土（含边沟）、装车、将土方弃运1km 、卸、空回、清理余土石方、施工防排水、挖台阶、修坡捡底、路拱成型、边坡修整挖装等全部工作内容。 | 人工费、材料费、机械费、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 按设计断面面积， 以天然方体积计算 |  |  |  | 10+500-12+300:82 12+300-12+440:1.5 1+260-1+380：0.2 T2+T3出口：1
3 | 其他机械开挖（渣场取料、便道维护等） | m3 | 130000 |  | 130000 | 挖土、装车、运输、卸土、修整、空回、清理余土等全部工序。 | 人工费、材料费、机械费、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 按设计断面面积， 以天然方体积计算 |  |  |  | B4渣土转运约3.2万
4 | 软石开挖 | m3 | 525781.92 |  | 525781.92 | 含石方破碎、挖装、1km 内运输、卸、检底（形成路拱及边沟）刷坡、清理余石、防尘、防排水处理等全部工作内容。（整体或者局部需要破碎的开挖) | 人工费、材料费、机械费、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 按设计断面面积， 以天然方体积计算
5 | 坚石爆破开挖 | m3 | 385242.81 | -210492.83 | 174749.98 | 要点封锁线路、警戒检查、消点开通线路、改装药包，处理盲炮，钻孔、装药、爆破、解小、清理，挖装、1km 内运输、卸、空回，检底（形成路拱及边沟）刷坡、清理余石、防尘、防排水处理等全部工作内容。 | 人工费、材料费（含火工品）、机械费、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 按设计断面面积， 以天然方体积计算
6 | 结构物基坑开挖 | m3 | 217533.06 |  | 217533.06 | 机械挖土至坑外50米内堆放，多余土方运至工程师指定位置，刷坡、人工配合清理基底、修正基底、防排水及安全防护等全部工作内容。 | 人工费、材料费、机械费、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 以现场实际完成的设计（或变更设计）内的基坑开挖天然方体积计算
7 | 路基填筑 | m3 | 1211095.285 | 181238.42 | 1392333.705 | 分层摊铺、平整、压实、临时排水、边坡（含路拱和水沟）修整、填料粒径分拣、厚度自检、压实度自检、取水洒水或翻晒、清理余土等全部工序的工作。 | 人工费、除土工材料外的所有材料费、机械费(含油料费）、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 按设计断面面积以压实方方体积计算
8 | 基坑回填 | m3 | 89200 |  | 89200 | 挖运土石方，分层摊铺、平整、夯实、临时排水、填料粒径分拣、厚度自检、压实度自检、取水洒水或翻晒、清理余土等全部工序的工作。 (含各类基坑及墙台背回填) | 单价包含除材料的全部费用。 | 以现场回填前实测尺寸体积与设计图示尺寸体积取小者计算
9 | 抛石防护 | m3 | 48829.85 | -10367.31 | 38462.54 | 施工准备，搭、找平，选修片石/块石，装片石/块石，安砌、包裹土工布；场内材料运输、清理等全部工作内容。 | 人工费、材料费（除片石/块石、土工布外）、机械费、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 按实际施工砌体尺寸计算体积
10 | 超距离运输 | m3.km | 4139306.19 |  | 4139306.19 | 土石方超过1km以外运输的相关全部工作。 | 人工费、材料费、机械费、运杂费、水电费、临时设施费、文明施工、综合管理费、安全防护及其他一切费用。 | 按设计断面面积，挖方以天然方体积乘以超运距离计算，借土填方按压实方乘以超运距离计算
BC-01 | 级配碎石填筑 | m3 |  | 138090.8 | 138090.8 | 施工准备，分层摊铺、推平、碾压、整平，养护，路面及边坡修整等全部工作内容 | 单价（除级配碎石混合料外）全部费用 | 按路基设计图示压实断面方计算
工程部负责人： |  |  |  |  | 项目总工：

## 路基分段土石方统计表 (hidden)
段落 | 挖填性质 | 起点 | 终点 | 长度 | 设计数量 | 小计
第1段 | 填方 | 0 | 3923 | 3923 | 641628.3 | 1369005.6242
| 挖方 |  |  |  | 181963.51 | 965220.0053
| 抛石 |  |  |  | 33628.98 | 38462.54
第2段(T1隧道) | 填方 | 3923 | 5314.7 | 1391.7 | 29156.95
| 挖方 |  |  |  | 326078.648
第3段 | 填方 | 5314.7 | 8560 | 3245.3 | 500691.5378
| 挖方 |  |  |  | 323755.42
| 抛石 |  |  |  | 4833.56
第4段 | 填方 | 8560 | 9545 | 985 | 14948.26 | 三工区
| 挖方 |  |  |  | 124268.96
第5段(T3隧道) | 填方 | 9545 | 9980 | 435 | 3495.24
| 挖方 |  |  |  | 63138.2
第6段 | 填方 | 9980 | 10160 | 180 | 4884.58
| 挖方 |  |  |  | 29657
第7段 | 填方 | 10160 | 12720 | 2560 | 109055.77
| 挖方 |  |  |  | 1090258.65
第8段（支线） | 填方 | 0 | 5003 | 5003 | 197528.8364
| 挖方 |  |  |  | 133422.4273
注意：不含桥梁墩台挖方！
备注：该图片为2024年度结算的三量对比表格
2095032.35